##### Case Study Exercise #12

Manage Metrics

Instructor’s Notes

The following information can be used to create metrics for the exercise

- Total project duration is eighteen months (all modules – need to estimate the duration of the first phase of A/R and Billing System implementation).

  - Project estimated end date vs. actual end date

  - Add duration for approved scope changes to the originally estimated end date

  - Capture from calendar, based on implementation date, or date when the customer signed off system as complete. (Reasonable to collect.)

- The budget for this project is $600,000 USD (or whatever number the team came up with).

  - Project estimated budget vs. actual budget

  - Add budget for approved scope changes to the originally estimated end date

  - Capture from company financial reports (Reasonable to collect).

- A similar metric can be defined for effort hours

  - Project estimated effort hours vs. actual effort hours

  - Add effort hours for approved scope changes to the originally estimated end date

  - Capture from time reporting system if available (Reasonable to collect)

  - If no time reporting system, capture manually (May or may not be reasonable to collect.)

- The project team is asked to document all the steps they go through in the implementation.

  - Does the document meet the completeness and correctness criteria (Reasonable to collect)

  - Is the customer satisfied with this document, survey (Reasonable to collect.)

- The online portion of this system must be up 99% of the time (or more).

  - Keep track of all downtime and calculate whether you achieved 60 minutes or less each month (Reasonable to collect).

- Nightly reports (printed and online) must be available by no later than 8:00 AM each morning.

  - Keep track of when reports were created through an automated process. (May or may not be reasonable to collect. Depends on whether the automation exists already or must be built.)

  - Look at trouble tickets to see if any reported instances of reports not being ready. (Reasonable to collect.)

- The system must strive for 100% accuracy in the invoices before they are mailed to the customer.

  - Count the number of errors from a manual spot check, vs. the total number of invoices going out. (Reasonable to collect.)

  - Number of customer complaints related to bad invoice vs. the total number of invoices going out. (Reasonable to collect.)

- Customer inquiries and problems must be resolved within 48 business hours.

  - Use features in problem tracking system to calculate number of hours between time the ticket was opened and closed. (Reasonable to collect.)

  - Send survey to customers who submit problems to see if they are satisfied with the overall resolution time. (Might be reasonable).

  - Track the numbers manually. (Probably not reasonable.)

- In addition, although not mentioned, the team should survey the customer for their satisfaction with the deliverables (A/R and Billing System) and their satisfaction with the performance of the project team.

  - Satisfaction surveys (Reasonable to collect.)

- Our customer service representatives must be helpful, courteous, knowledgeable and professional.

  - Customer satisfaction survey (Reasonable to collect)

  - Follow-up focus groups (Might not be reasonable)

  - Independent rating of call conversation (Reasonable to collect)

- The initial customer service representative will retain ownership of any outstanding problems until they are resolved.

  - Customer satisfaction survey after the problem is closed (Reasonable to collect).

  - Independent rating of call conversation (Reasonable to collect)