Case Study Exercise #3

Approach

At a high-level, the project will be implemented using a traditional “waterfall” development approach. The Analysis Phase will be followed by a Design Phase, Construct Phase, Testing Phase and Implementation Phase.

The Analysis Phase will start with an identification of the key stakeholders. These stakeholders will be invited to a four-day facilitated session to discuss how the business processes work today and how they would like to see the business processes work in the future. A gap analysis will then be created that shows what needs to happen to move from the current environment to the new one. After the facilitated session, all the findings will be documented and distributed back to the meeting participants for revisions. All the documents will be updated based on stakeholder feedback and then presented to the sponsor for approval.

After the facilitated session, but while the notes are being distributed for feedback, the project team can begin to create three high-level strategy documents that will help to set future direction. The Testing Strategy, Training Strategy and Implementation Strategy will be created at this time. Each of these documents will be written in a draft form, circulated to the appropriate stakeholders, modified based on their feedback and then approved by the project sponsor.

Since the project team knows the financial package they are implementing, they can begin work setting up the computer test environment at any time during the Analysis Phase. They will need to identify a contact with the vendor to help create the environment. There will be an all-day planning session to define the environment. Then hardware and system software will need to be ordered. All this work needs to be done before the Analysis Phase is completed.

Case Study Exercise #4 - Estimating

Estimate the effort hours required to

- Conduct the facilitated session

- Complete the three strategy documents

- Determine the proper computer environment

- Complete the entire Analysis Phase (Not all detailed activities are included below.)

Use the following information:

- Historical trends indicate that a project should spend 30% of its time in the Analysis Phase

- The project manager discussed this effort with four companies who previously implemented this same financial package.

- Company A took 1200 hours to complete the entire project

- Company B is a similarly sized company to ours. They stated that the entire implementation project took 3600 hours

- Company C is about twice as large as our company, and processes about twice as many transactions as we do. They took 1800 hours to complete the Analysis Phase.

- The vendor thinks that the project will take around 2700 hours, plus or minus 20%.

- Our sponsor says that we have funding for 1200 hours to complete the entire project. If it takes more than that, he will need to seek additional funding.

- The Institute of Facilitators says that for every day to teach a facilitated session, it takes a half-day of preparation and a half-day to recap and document the results. There will be two team members facilitating the initial session

- After looking at the various sections of the Testing Strategy, one of the team analysts estimated the work to be 60 hours, plus 25% for rework based on feedback. This same analyst thought that the Training Strategy would take approximately half the time as the Testing Strategy

- There is an employee who has done a number of Implementation Strategy documents before. She says that we should be able to create this document in 40 hours.

- The all-day session to determine the computer environment will be a facilitated session, with one team member as the facilitator and two team members attending.

- Company C had to set up the same computer environment that we are creating. They said that they would give us any documentation they have on how they set their environment up.

Case Study Exercise #4 - Estimating

Instructors Notes

The time to complete the Analysis Phase

- Historical trends indicate that a project should spend 30% of its time in the Analysis Phase. (Historical trend)

- The project manager discussed this effort with four companies who previously implemented this same financial package.

- Company A took 1200 hours to complete the entire project. (This is not included in the estimating process. There is no basis for comparison since you do not know the relative complexity and size of this project.)

- Company B is a similarly sized company to ours. They stated that the entire implementation project took 3600 hours. (Analogy – the Analysis might be 3600 * .30 = 1080 hours)

- Company C is about twice as large as our company, and processes about twice as many transactions as we do. They took 1800 hours to complete the Analysis Phase. (Ratio – 1800 * .5 = 900 hours for Analysis)

- The vendor thinks that the project will take around 2700 hours, plus or minus 20%. (Expert Opinion – 2700 * .30 = 810 hours +/- 162 hours (20%))

- Our sponsor says that we have funding for 800 hours to complete the entire project. If it takes more than that, he will need to seek additional funding. (Not relevant to the estimating process)

Overall input for estimate is 810 (+/- 162), 900 and 1080 hours. A good average estimate might be anywhere in the range of 930 hours, which is the average.

The time for the team to conduct the facilitated session

- The Institute of Facilitators says that for every day to teach a facilitated session, it takes a half-day of preparation and a half-day to recap and document the results. There will be two team members facilitating the initial session. (Parametric and expert opinion - 4 days * 2 people = 8 days. Add 2 days for preparation and 2 days for recap. Total is 12 days or 96 hours.)

The time to complete the three strategy documents

- After looking at the various sections of the Testing Strategy, one of the team analysts estimated the work to be 60 hours, plus 25% for rework based on feedback. (Expert opinion – 60 * 1.25 = 75 hours)

- This same analyst thought that the Training Strategy would take approximately half the time as the Testing Strategy (Expert opinion, ratio – 75 * .5 = 37.5 hours).

- There is an employee who has done a number of Implementation Strategy documents before. She says that we should be able to create this document in 40 hours. (Expert opinion – 40 hours. Might factor up a little, since it may take longer because your team has not done it before.)

The time to determine the proper hardware and software needed.

- The all-day session to determine the computer environment will be a facilitated session, with one team member as the facilitator and two team members attending. (WBS, expert opinion – Facilitator for eight hours, plus 4 hours prep and 4 hours recap – 16 hours. Two team members for 8 hours each. Total time is 32 hours)

- Company C had to set up the same computer environment that we are creating. They said that they would give us any documentation they have on how they set their environment up. (Historical estimate – If this is a good document, the final estimate for this work may be substantially reduced, based on having this information available)